## Tabelle1
Project name: |  |  |  | Team 1 "DBP-DSS-Microservice"
Vorgehensweise: agil
Teammitglieder: Thomas Berthold, Romy Franz, Abdell Kaouch, Richard Lorenz, Sören Taube
Rollenverteilung: nicht stikt, Schwerpunkte: Projektleitung: Thomas Berthold, Coding: Richard Lorenz, Sören Taube, QM: Romy Franz
KW |  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Datum |  |  | 10.4.-16.4. | 17.4.-23.4. | 24.04.-30.4. | 1.5.-7.5. | 8.5.-14.5. | 15.5.-21.5. | 22.5.-28.5. | 29.5.-4.6. | 5.6.-11-6. | 12.6.-18.6. | 19.6.-25.6. | 26.6.-2.7. | 3.7.-9.7. | 10.7.-16.7.
Project Management
| Project planning | Work packages, process, deadlines, resource allocation, (costs) | bar: 15 to 18
| Project controlling | target-performance comparison, management activities | bar: 17 to 25
| Project closure | Final calculation, handover/presentation, complete archiving | bar: 25 to 27
Project Owner / Tutor
| Review and feedback | on-side or video call | bar: 18; 21; 24; 27
| Handover and instruction in source code | collaborative opening: source code project in IDE, build and run | bar: 24; 27
| Final presentation | Meeting on-side | bar: 27
Problem formulation
| Industrial problem/issue/needs | Reports what the problem is, where it occours, and who observed it | bar: 15 to 18
| Context | Reports environments factors such as settings and locations | bar: 16 to 17
| Research questions with priority | Research questions or similar | bar: 17 to 18
| Contact persons | academic and industrial | bar: 16
| Literature Search | Systematic literature review OR systemic mapping study
| Planning the review | SLR RQ's, Keywords, inclusion/exclusion criteria, Data extraction table | bar: 16 to 21
| Conducting the review | search, selection, extraction, synthesis | bar: 17 to 21
| Reporting the review | quantitative summary results in tables, discussion of principal findings | bar: 19
| Implications for own development | Approaches available? Ideas, requirements, input … | bar: 19
| Software Development | Candidate Solution, developed in close collaboration (industrial partner)
| Prepare IDE and tools | development environment | bar: 16 to 17
| Agile development | Backlog, refinements, sprint (plan, do, review), version control, release | bar: 18 to 21
| Testing | Bugtracking, Bugfixing, … | bar: 19 to 23
| Documentation | Screenshots and screenvideos embedded in documents & presentations | bar: 21 to 23
| Release as open source project | Publication via tutor | bar: 22 to 23
Software Deployment
| Prepare stage/production environment | Environment on which to deploy the releases | bar: 17 to 18
| Test deploy | Test cases, test protocols, test | bar: 18
| Deploy release | stage/production will be updated | bar: 19; 22
| Software configuration management | configuration data versioning | bar: 18 to 19; 22; 26
| Release as open data project | git hub or researchgate via tutor | bar: 23; 27